## Desk Reservation
SINO | Feature Name/High Level Function | Description | UI Changes | UI Fields | UI Estimation in Man/Days(8 hours) | API Changes | Backend Changes | Assumption | API Estimation in Man/Days(8 hours) | criticality
1 | Login | System should all the authorized user to Dashboard otherwise it will display error message | Develop login screen | Employee Mail Id Corp Key | 1 | Develop authentication API to validate Develop API to fetch the use details from active directory. |  | User authentication will happened through ING active directory | 2 | Medium
2 | Display Dashboard | Successfully authenticated user will be landing to Dashboard | Develop Dashboard UI to display the list of existing buildings details. | List of build name with link | 1 | No | No | No | NA | Low
| ING Workspace Booking Page | After clicking any of the building, user reach to this page | Develop ING Workspace Booking Page with couple of link for reservation and support. | Below Labels: Assistant Preferences About Feedback Share | 2 |  |  |  | NA | Medium
| Preference Screen | After clicking preference link, user reach to preference page | Develop preference screen to provide user input for the reservation. Validate user input like date and time | Type of reservation Building View Date Start Time End Time | 2 | Develop API to get the reservation rule from back end system. Validate user input with reservation rule. Persist the user reservation details in the back end system. | DB model to provide reservation rule. DB model to persist the user reservation details. | Reservation rule will be available in the same application and not getting from external API. | 3 | Medium
| My Desk Reservation Page | After providing reservation details, and click save button then system takes into "My Desk Reservation" page. It will display list of future reservation in the right top window, list of present desk reservation details in the left top window, and list of past desk reservation details in the left bottom window. In addition there are few button in the bottom of the screen like My Desk Reservation, ING Building Map and Quick Pick Desk. Note: Each window will display below details: Date, start time, end time, desk and building. | Develop My Desk Reservation Page to provide user reservation details. | Below fields to be displayed the 3 panel(left, right,bottom): Date Start Time End Time Desk Name Building Name | 3 | Develop API to fetch the current reservation details. Develop API to fetch the future reservation details. Develop API to fetch the past reservation details. | Use existing DB model to cancel reservation details. |  | 5 | High
| Cancel Reservation Page | when user clicks future or current reservation (Single selection), it takes into cancel screen | Develop UI to display the reservation details to cancel it. | Display Reservation details as below: Desk Name Employee mail id Date Start Time End Time Cancel button | 2 | Develop API to cancel the reservation | Use existing DB model to cancel reservation details. |  | 2
| ING Building Map | Develop UI to display the building map. | Develop UI to display building map. | Display building map fetched from API | 2 | Develop API to pull the API building map from external system that maintain the build map details. | NO | It is indeed bit complex integration to display the building details. | 6 | High
|  | User select the building & Display list of floor available in the selected building. | Provide link to building & Display building details | Display list of floors in the right side map. | 1 | Develop API to provide the list of floors available in the selected building. | Create a DB model to provide the building and floor details. | The building and floor details will be feeding in the backend. | 4
|  | Display floor details like list of desk available in the floor | Display list of desk available in the floor. | Display list of desk available by hight lighting as green . Once desk is selected then , it will highligh as red. | 3 | Develop API to provide to get the list of desk details in the selected floor. | Create a DB model to provide the desk details for selected floor. | The desk and floor details will be feeding in the backend. | 2
|  | Display selected desk details | Display selected desk detail by high lighting red for selected floor. | Display desk details like alredy reserved details in a list followed by the current reservation : Desk Name Floor No Room No | 3 | Develop API to provide the desk details like provide already reserved details etc.. | Create a DB model to provide the desk details for selected desk. | The desk and floor details will be feeding in the backend. | 3
| Make Reservation | User click the add button in the desk details page, it will display reservation details like desk name , user name , reservation time that is selected in the preference screen. | Display reservation details screen by displaying field like desk name , user name , reservation time that is selected in the preference screen. | Display Reservation details as below: Desk Name Employee mail id Date Start Time End Time Cancel button | 1 | Develop API to store reservation details | Use existing DB model to store reservation details. |  | 2
| QuickPickDesk | Display list of available desk details irrespective of the floor. | Develop UI to display the list of available desk details in the screen. | Display list of desk name as label | 1 | Develop API to fetch the list of available desk irrespective of the floor. | Develop a model to store the desk , floor and build details. |  | 2
|  | Display selected desk details | Develop UI to display the selected desk details in the screen. | Display Reservation details as below: Desk Name Employee mail id Date Start Time End Time Cancel button | 1 | Validate the selected reservation is available or not. If not available the send the error message back to UI. If available then use existing API to store reservation details | Use existing DB model to store reservation details. |  | 2
|  | User click cancel button the system, go back to QuickPickDesk screen. | Create the Cancel button and provide a link to go back to QuickPickDesk screen. | Provide link to back to screen | 1 | NA
| CheckIn-CheckOut | User use the check in and check out functionality to perform those activities for those booked reservations. | Develop UI to display Check-in & Checkout for already booked reservations . | Ad two button for check-in and check-out | 1 | Develop API to update the already booked reservations for their check-in and Check out | Modify the existing DB model to store check-in and Check out details. |  | 2
| Admin Screen | Admin screen used to update the reservation details such as update the working hours and add or modifying the building or floor or desk details | Develop UI to modify reservation details like working hours and add or modifying the building or floor or desk details | Update below fields Number of working hours add/update/delete building/floor/desk name | 4 | Develop API to update the already available reservation details | Use existing DB model |  | 4
| Stake discussion |  |  |  | 2 |  |  |  | 2
| Integration & Functional Tseting |  |  |  | 15 |  |  |  | 15
| Build and Deployment |  |  |  | 10 |  |  |  | 10
| Report |  |  |  | 5 |  |  |  | 5

## Room Reservation
SINO | Feature Name/High Level Function | Description | UI Changes | UI Fields | UI Estimation in Man/Days(8 hours) | API Changes | Backend Changes | Assumption | API Estimation in Man/Days(8 hours) | criticality
1 | Login | System should all the authorized user to Dashboard otherwise it will display error message | Develop login screen | Employee Mail Id Corp Key | 1 | Develop authentication API to validate Develop API to fetch the use details from active directory. |  | User authentication will happened through ING active directory | 2 | Medium
2 | Display Dashboard | Successfully authenticated user will be landing to Dashboard | Develop Dashboard UI to display the list of existing buildings details. | List of build name with link | 1 | No | No | No | NA | Low
| ING Workspace Booking Page | After clicking any of the building, user reach to this page | Develop ING Workspace Booking Page with couple of link for reservation and support. | Below Labels: Assistant Preferences About Feedback Share | 2 |  |  |  | NA | Medium
| Preference Screen | After clicking preference link, user reach to preference page | Develop preference screen to provide user input for the reservation. Validate user input like date and time | Type of reservation Building View Date Start Time End Time | 2 | Develop API to get the reservation rule from back end system. Validate user input with reservation rule. Persist the user reservation details in the back end system. | DB model to provide reservation rule. DB model to persist the user reservation details. | Reservation rule will be available in the same application and not getting from external API. | 3 | Medium
| My Desk Reservation Page | After providing reservation details, and click save button then system takes into "My Desk Reservation" page. It will display list of future reservation in the right top window, list of present desk reservation details in the left top window, and list of past desk reservation details in the left bottom window. In addition there are few button in the bottom of the screen like My Desk Reservation, ING Building Map and Quick Pick Desk. Note: Each window will display below details: Date, start time, end time, desk and building. | Develop My Desk Reservation Page to provide user reservation details. | Below fields to be displayed the 3 panel(left, right,bottom): Date Start Time End Time Desk Name Building Name | 3 | Develop API to fetch the current reservation details. Develop API to fetch the future reservation details. Develop API to fetch the past reservation details. | Use existing DB model to cancel reservation details. |  | 5 | High
| Cancel Reservation Page | when user clicks future or current reservation (Single selection), it takes into cancel screen | Develop UI to display the reservation details to cancel it. | Display Reservation details as below: Desk Name Employee mail id Date Start Time End Time Cancel button | 2 | Develop API to cancel the reservation | Use existing DB model to cancel reservation details. |  | 2
| ING Building Map | Develop UI to display the building map. | Develop UI to display building map. | Display building map fetched from API | 2 | Develop API to pull the API building map from external system that maintain the build map details. | NO | It is indeed bit complex integration to display the building details. | 6 | High
|  | User select the building & Display list of floor available in the selected building. | Provide link to building & Display building details | Display list of floors in the right side map. | 1 | Develop API to provide the list of floors available in the selected building. | Create a DB model to provide the building and floor details. | The building and floor details will be feeding in the backend. | 4
|  | Display floor details like list of desk available in the floor | Display list of desk available in the floor. | Display list of desk available by hight lighting as green . Once desk is selected then , it will highligh as red. | 3 | Develop API to provide to get the list of desk details in the selected floor. | Create a DB model to provide the desk details for selected floor. | The desk and floor details will be feeding in the backend. | 2
|  | Display selected desk details | Display selected desk detail by high lighting red for selected floor. | Display desk details like alredy reserved details in a list followed by the current reservation : Desk Name Floor No Room No | 3 | Develop API to provide the desk details like provide already reserved details etc.. | Create a DB model to provide the desk details for selected desk. | The desk and floor details will be feeding in the backend. | 3
| Make Reservation | User click the add button in the desk details page, it will display reservation details like desk name , user name , reservation time that is selected in the preference screen. | Display reservation details screen by displaying field like desk name , user name , reservation time that is selected in the preference screen. | Display Reservation details as below: Desk Name Employee mail id Date Start Time End Time Cancel button | 1 | Develop API to store reservation details | Use existing DB model to store reservation details. |  | 2
| QuickPickDesk | Display list of available desk details irrespective of the floor. | Develop UI to display the list of available desk details in the screen. | Display list of desk name as label | 1 | Develop API to fetch the list of available desk irrespective of the floor. | Develop a model to store the desk , floor and build details. |  | 2
|  | Display selected desk details | Develop UI to display the selected desk details in the screen. | Display Reservation details as below: Desk Name Employee mail id Date Start Time End Time Cancel button | 1 | Validate the selected reservation is available or not. If not available the send the error message back to UI. If available then use existing API to store reservation details | Use existing DB model to store reservation details. |  | 2
|  | User click cancel button the system, go back to QuickPickDesk screen. | Create the Cancel button and provide a link to go back to QuickPickDesk screen. | Provide link to back to screen | 1 | NA
| CheckIn-CheckOut | User use the check in and check out functionality to perform those activities for those booked reservations. | Develop UI to display Check-in & Checkout for already booked reservations . | Ad two button for check-in and check-out | 1 | Develop API to update the already booked reservations for their check-in and Check out | Modify the existing DB model to store check-in and Check out details. |  | 2
| Admin Screen | Admin screen used to update the reservation details such as update the working hours and add or modifying the building or floor or desk details | Develop UI to modify reservation details like working hours and add or modifying the building or floor or desk details | Update below fields Number of working hours add/update/delete building/floor/desk name | 4 | Develop API to update the already available reservation details | Use existing DB model |  | 4
| Stake discussion |  |  |  | 2 |  |  |  | 2
| Integration & Functional Tseting |  |  |  | 15 |  |  |  | 15
| Build and Deployment |  |  |  | 10 |  |  |  | 10
| Report |  |  |  | 5 |  |  |  | 5